## Developer Work Packages
WP ID | Capability ID | Epic | Title | Wave | Priority | Depends On | Bible Refs | GPMA Refs | Inputs | Outputs | Acceptance Criteria | Test Suite | Owner | Status
WP-0001 | FND-001 | Foundation | Create Monorepo Skeleton | 1 | P0 |  | Vol0 Part XI; Repository Constitution | GPMA-001 | Repository | Working monorepo | Build passes; CI configured | Build/CI tests | Platform | Ready
WP-0002 | FND-002 | Foundation | Canonical Object Model | 1 | P0 | WP-0001 | Vol0 Parts II, III | GPMA-001 | Ontology | Core object library | Schemas compile; serialization works | Schema tests | Foundation | Ready
WP-0003 | FND-003 | Foundation | Ontology Engine | 1 | P0 | WP-0002 | Vol0 Part II | GPMA-001 | Ontology | Ontology service | Queries resolve entities | Ontology tests | Foundation | Ready
WP-0004 | FND-004 | Foundation | Graph Engine | 1 | P0 | WP-0002 | Vol0 Part III | GPMA-001 | Canonical objects | Graph API | Traversal + persistence | Graph tests | Foundation | Ready
WP-0005 | GEN-001 | Genesis | Observation Engine | 2 | P0 | WP-0003 | Vol0 Part XV | GPMA-001 | Raw observations | Observation Graph | Ingests normalized observations | Ingestion tests | Genesis | Ready
WP-0006 | GEN-006 | Genesis | Recursive System Expansion | 3 | P0 | WP-0004,WP-0005 | Vol0 Parts III, XIII, XV | GPMA-001 | Observation Graph | Expanded System Graph | Recursive expansion matches design | Replay tests | Genesis | Planned
WP-0007 | GEN-009 | Genesis | Constraint Discovery | 3 | P0 | WP-0006 | Vol0 Part IX | GPMA-001 | Expanded Graph | Constraint Graph | Known bottlenecks detected | Historical replay | Genesis | Planned
WP-0008 | GEN-010 | Genesis | Bottleneck Discovery | 3 | P0 | WP-0007 | Vol0 Part IX | GPMA-001 | Constraint Graph | Bottleneck Graph | Ranks bottlenecks | Regression tests | Genesis | Planned
WP-0009 | PRO-001 | Prometheus | Economic Digital Twin | 4 | P0 | WP-0008 | Vol0 Parts VI, XIII | GPMA-001 | Published graphs | Digital Twin | Twin updates correctly | Scenario tests | Prometheus | Planned
WP-0010 | PRO-004 | Prometheus | Investment Thesis Builder | 4 | P0 | WP-0009 | Vol0 Part X | GPMA-001 | Digital Twin | Investment Thesis | Traceable thesis | Acceptance suite | Prometheus | Planned