## Backlog
Epic | Capability ID | Capability | Priority | Wave | Dependencies | Owner | Status
Foundation | FND-001 | Monorepo & Repository Layout | P0 | 1 |  | Platform | Planned
Foundation | FND-002 | Canonical Object Model | P0 | 1 | FND-001 | Foundation | Planned
Foundation | FND-003 | Ontology Engine | P0 | 1 | FND-002 | Foundation | Planned
Foundation | FND-004 | Graph Engine | P0 | 1 | FND-002 | Foundation | Planned
Foundation | FND-005 | Scientific Memory | P0 | 1 | FND-004 | Foundation | Planned
Genesis | GEN-001 | Observation Engine | P0 | 2 | FND-003 | Genesis | Planned
Genesis | GEN-002 | Evidence Engine | P0 | 2 | GEN-001 | Genesis | Planned
Genesis | GEN-003 | Signal Discovery | P0 | 2 | GEN-002 | Genesis | Planned
Genesis | GEN-004 | Theme Discovery | P0 | 3 | GEN-003 | Genesis | Planned
Genesis | GEN-005 | Megatrend Discovery | P0 | 3 | GEN-004 | Genesis | Planned
Genesis | GEN-006 | Recursive System Expansion | P0 | 3 | GEN-004,FND-004 | Genesis | Planned
Genesis | GEN-007 | Value Chain Discovery | P0 | 3 | GEN-006 | Genesis | Planned
Genesis | GEN-008 | Tier-N Supply Chain Discovery | P0 | 3 | GEN-007 | Genesis | Planned
Genesis | GEN-009 | Constraint Discovery | P0 | 3 | GEN-008 | Genesis | Planned
Genesis | GEN-010 | Bottleneck Discovery | P0 | 3 | GEN-009 | Genesis | Planned
Genesis | GEN-011 | Profit Pool Migration | P0 | 3 | GEN-010 | Genesis | Planned
Genesis | GEN-012 | Historical Analog Engine | P0 | 3 | GEN-011 | Genesis | Planned
Genesis | GEN-013 | Economic Law Discovery | P0 | 3 | GEN-012 | Genesis | Planned
Prometheus | PRO-001 | Economic Digital Twin | P0 | 4 | GEN-013 | Prometheus | Planned
Prometheus | PRO-002 | Scenario Engine | P1 | 4 | PRO-001 | Prometheus | Planned
Prometheus | PRO-003 | Causal Inference Engine | P0 | 4 | PRO-001 | Prometheus | Planned
Prometheus | PRO-004 | Investment Thesis Builder | P0 | 4 | PRO-003 | Prometheus | Planned
Prometheus | PRO-005 | Timing Engine | P1 | 4 | PRO-004 | Prometheus | Planned
Prometheus | PRO-006 | Risk Engine | P1 | 4 | PRO-004 | Prometheus | Planned
CIO | CIO-001 | Portfolio Construction | P1 | 5 | PRO-004 | CIO | Planned
CIO | CIO-002 | Position Sizing | P1 | 5 | CIO-001 | CIO | Planned
CIO | CIO-003 | Monitoring & Alerts | P1 | 5 | CIO-001 | CIO | Planned
Platform | PLT-001 | Workflow Orchestrator | P0 | 1 | FND-001 | Platform | Planned
Platform | PLT-002 | Event Bus | P0 | 1 | PLT-001 | Platform | Planned
Platform | PLT-003 | Replay Framework | P0 | 2 | PLT-002 | Platform | Planned